## Checklist Details
Title | Details
Checklist name | LT_Mini_Pillar
Category | LT
Subcategory | Mini Pillar
Description
Site | IIM Ahmedabad
Started by | Dhruvit
Started On | Aug 12, 2026, 12:29 PM
Status | Completed
Location | 0,0
Completed by | Dhruvit
Completed on | Aug 12, 2026, 12:29 PM
Created by | Dhruvit
Created on | Aug 12, 2026, 11:19 AM

## Basic Details
Section | Title | Answer | Measurement | Notes | Images | Videos | Documents
Basic Details | SAP Code | 10460112
Basic Details | Vendor Name | ABB India Limited
Basic Details | Offered Qty | 40 Nos
Basic Details | PO Details | PO No. 4500131022 dated 18-Jun-2026
Basic Details | AEML Engineer & Designation | Ankit Mehta, Assistant Engineer (Projects)
Basic Details | Vendor Engineer & Designation | Deepak Joshi, Senior Quality Inspector
Basic Details | Sl Nos of Items | AEML-MP-2607-001 to AEML-MP-2607-040
Basic Details | Date of Inspection | Aug 12, 2026

## Characteristics _ Parameter
Section | Title | Input | Measurement | Notes | Images | Videos | Documents
Visual & Physical Checks | Dimensions | Ok |  | Overall H×W×D verified on 3 samples — OK.
Visual & Physical Checks | Sheet Steel Thickness & Type | Canopy -3mm¦Others 2mm- OK
Visual & Physical Checks | Electrical Clearances | Ok
Visual & Physical Checks | Earthing | Ok
Visual & Physical Checks | Paint Shade & Thickness | Ok |  | Powder coat DFT checked at 5 points — within spec.
Visual & Physical Checks | Gland Plate- Hole Size and Knockouts | Ok
Visual & Physical Checks | Hardware | Not Ok
Visual & Physical Checks | Door Hinges /Interlock for door removal from hinge | Ok |  | Hinge interlock operates smoothly; door removal checked.
Visual & Physical Checks | Locking Arrangement | Not Ok |  | Cam lock not engaging fully on rear door.
Visual & Physical Checks | Danger Boards | Not Ok
Visual & Physical Checks | Foundation Structure | Ok
BOM Verification | Bill of Material | Ok
Fabrication & Manufacturing Quality Checks | Welding | Not Ok
Fabrication & Manufacturing Quality Checks | Finishing & Painting | Not Ok
Raw Material / Bought out Items TC Verification | TC of GI sheet from raw material sub vendor | Ok
Raw Material / Bought out Items TC Verification | Bus Bar Conductivity | Ok |  | Al bus bar TC from mill attached.
Photos Upload | All 4 sides view with door closed condition | Not Attached
Photos Upload | Door Open Views Front & Back | Attached
Photos Upload | Foundation Structure View | Not Attached
Acceptance Tests as per QAP/IS | Insulation resistance test phase to phase & phase to earth | Ok |  | Test aborted — surface moisture; dry & retest required.
Acceptance Tests as per QAP/IS | High voltage test | Ok |  | HV withstand at specified kV for 1 min — no flashover.
Acceptance Tests as per QAP/IS | Powder coating thickness measurement | Not Ok
Acceptance Tests as per QAP/IS | Al Bus Bar conductivity measurement | Ok
Other Compliances for Manufacturing Facility | Safety Aspects in Facility | Ok
Other Compliances for Manufacturing Facility | House Keeping | Ok |  | Staging area orderly; material segregated.
Other Compliances for Manufacturing Facility | Eco-friendly Waste Segregation, Collection and Storage Practices w.r.t Hazardous / Non-Hazardous Materials | Not Ok
Other Compliances for Manufacturing Facility | Calibration of Testing Instruments | Not Ok
Other Compliances for Manufacturing Facility | SA 8000 Compliance | Not Ok

## Inspection Observations
Section | Observations | Answer | Measurement | Notes | Images | Videos | Documents
Default | 1. | Gland plate knockout sizes verified against cable schedule; one spare knockout to be blanked before dispatch.
Default | 2 | Danger board fixing found loose on two units; re-fixed with spring washers and verified.
Default | 3 | Foundation bolt hole pitch matches approved civil drawing; no rework required.

## Inspection Conclusion
Section | Title | Answer | Measurement | Notes | Images | Videos | Documents
Inspection Summary | Test Results | Not Ok |  | All acceptance tests Pass as recorded above.
Inspection Summary | Technical Clearance | Yes
Inspection Summary | Declaration | Acceptance tests / visual checks not meeting specification. Material is rejected for the offered lot.